## Tasks
Task ID | Task | Description | Time(h) | Issues
1 | Domain modelling | Identify domain entities and its relationships | 1
2 | Develope domain model | Develop POJOs and corresponding annotations | 5 | Circular loop due to cart field not declare in @Equalsandhash annotation
3 | Develope entity test model | Develop unit tests | 4
4 | Develope service | Business logic, create Cart, get existing Cart, add items to Cart and delete Cart | 6 | Trying to implement Optionals wherever was possible
5 | Develope service test | Develop unit tests | 6 | First time mocking service
6 | Develope controller | Expose business service via HTTP | 6 | Simplify logic using Optionals and Lambda expressions
7 | Develope controller test | Expose business service throughout HTTP protocol and | 5 | Explore Mockito framework in more detail
8 | Develope caching and TTL | Cache cart data and implement 10 minutes TLL | 2
9 | Investigate SpringBoot |  | 5
10 | Document API | https://documenter.getpostman.com/view/12183878/2s8YzZPKBW#b321656a-387a-4e7b-aad3-897c7923c4b3 | 1
Total |  |  | 41